## Slide 1: Projektový management
Blok 2

## Slide 2: Plán pro dnešek
Úvod a individuálních tvorba příkladu na LRM (cca 30 minut)
Rady k realizační části úkolu v Promisu (cca 20 minut)
1. část o zahájení a řešení rozsahu projektu atd. (cca 50 minut)
pauza
2. část o plánování času, řešení rizik atd. (cca 50 minut)
3. část o řízení a kontrole i ukončení projektu (cca 50 minut)
Notes: - Produktivita nebo nižší náklady mohou pomoct záměru projektu (lepší publikace)

## Slide 3: Úkol na logickou rámcovou matici
Vzít si šablonu (soubory v MS Teams), vyplnit a do cca 16,35 nahrát do „Odevzdávárny“ (v IS v MKH_PRMG) pojmenované „Úkol 1 – LRM (5.12.)“.
Očekávání ohledně vyplnění:
alespoň 3 rozumné záměry se souvisejícími položkami
správně definovaný měřitelný cíl se souvisejícími položkami
rozpad na cca 4-6 výstupů se souvisejícími položkami
rozpad jednoho výstupu na 4-6 činností se správně vyplněnými souvisejícími položkami
u předpokladů alespoň tři položky patřící (logickou a věcnou provazbou) do daného řádku
alespoň tři rozumné věci, co projekt neřeší a tři podstatné předpoklady
Notes: What has changed in the last years that caused an increase in these challenges?
What new skills and competencies are required today?

## Slide 4: Rady k realizační části Promisu

## Slide 5: 1. část
Zahájení a plánování projektu

## Slide 6
PŘEDPROJEKTOVÁ FÁZE
Studie příležitosti
FÁZE ŘÍZENÍ PROJEKTU
Zahájení
POPROJEKTOVÁ FÁZE
Přínosy
Lessons learned
Studie proveditelnosti
Strategie
Plánování
Realizace + kontrola
Ukončení
Logický rámec
WBS
CPM
Analýza rizik
Analýza stakeholderů
Gantt

## Slide 7
Zahájení

## Slide 8: Minimum pro zahájení projektu
cíl – je dobře stanoven? Není vágní? Lze s tím ještě něco dělat?
zakládací listina projektu
  formalizuje existenci projektu – jak?
  přiděluje manažerovi projektu pravomoci pro použití zdrojů
  definuje odpovědnost manažera za naplnění požadavků projektu
přidělení zdrojů
kick – off meeting

## Slide 9
Plánování (1.část)

## Slide 11: Co je třeba plánovat?
výstupy (rozsah, hranice projektu)
technologii a metody
zdroje
náklady
čas
…
Notes: Co je plán (dotační a projektový, proč jsou dva atd. - podrobnosti ve 3. bloku)
- hlavně třeba času vypadá velmi snadno, když se popíše (rozpad prací > návaznosti a seřazení > časový odhad > doladění)

## Slide 12: Plánování rozsahu = Work Breakdown Structure (WBS)
CO chceme v projektu udělat? (ne JAK)
hranice projektu
definuje 100 % rozsahu projektu
na základě toho zjišťujeme JAK
cíl → výstupy → pracovní balíky
obrana proti „přetečení“ obsahu (scope creep)
Notes: Why to plan it?
Example: We need to transport all the equipment for the workshop – has to be defined clearly – roll-ups won´t fit into small car
Estimates often too quick (We will need 10 laptops for this project – how much does an average laptop cost? But they needed to use software for architects – additional demands for memory, graphic card etc.)
Scope creep – slow increase in the scope of the project

## Slide 14: WBS

## Slide 15: Je vaše WBS správně?
na nejnižší úrovni je vše, co je potřeba udělat k naplnění projektového cíle
je možné přiřadit odpovědnost za pracovní balíky
lze odhadnout náklady a čas pracovních balíků
lze měřit dokončenost pracovních balíků
zahrnuje náklady na Vás (projektového manažera)! (řízení a administraci projektu)

## Slide 16: RASCI matrix – pro velké projekty
R – responsible
A – accountable
S – support
C – consulted
I – informed
Notes: R – people who really do the job

## Slide 17: RASCI matrix
 | Noe | Manželka | Asistent
Sloni jsou na Arše | A | I | R
Lvi jsou na Arše | A | I | R
Vnitřní uspořádání lodi hotové | A,R | C | I
R – responsible
A – accountable
S – support
C – consulted
I - informed

## Slide 18: 2. část
Plánování projektu

## Slide 19
Plánování (2.část)

## Slide 20: Plánování času a zdrojů
JAK, ne CO
definuje v jakých termínech a časových sledech budou práce na projektu probíhat
aktivity založené na WBS nebo logickém rámci
Notes: zrada je v detailech, zejména ve vynechání prací (buď přílišný detail všeho anebo naopak nepřemýšlení nad tím, co vše práce obsahuje) a podcenění jejich obtížnosti.
Pak trochu v řazení (hlavně lead a lag) a rizicích spojených s kaskádovým "sesypáním" této návaznosti.
A nejvíce v odhadech času a tom, jak z někoho třetího/externího dostat realistický odhad času (a raději tři, než jeden) a navázat ten čas na jeho implicitní přepodklady (složitosti, podmínek, BIAS chyby atd.) a současně chápat implicitně vložené rezervy. Určitě naučit dělat plánovací poker (včetně diskuze těch, kteří dali minimum a maximum)

## Slide 21: Plánování času a zdrojů
Hlavní nástroje:
Ganttův diagram
    + přehlednost
    + jednoduchost konstrukce
    - neukazují přehledně závislosti mezi úkoly (činnostmi)
    - změna v délce jedné činnosti se většinou (automaticky) nepromítne do zbývající části
    CPM – critical path method – kritická cesta
    + souhrnně prezentuje souvislosti
    + umožňuje hledat alternativy
    + definuje kritickou cestu
    - složitost
    - nepřehlednost
The time is the only thing that cannot be bought

## Slide 22: Odhadování
Window method 
Top-down, Bottom-up
Groupe estimation technique (Delphi, Crawford´s slip etc.)
Expert guess (SME)
Comparative or analogous estimation
PERT – uses Three-point estimating
Planning poker
Plánovací poker
Notes: Expert guess – number of experts named, their estimates evaluated in a pre-defined way (top-down)
Simulation (Monte Carlo)
PERT – programme evaluation and review technique

## Slide 23: Odhadování - Three-point estimating
dobu trvání stanovují na základě optimistických, realistických a pesimistických variant odhadů trvání činností
Notes: Plánování, tři odhady, s tím, že plánovací poker bude v druhém bloku

## Slide 24: Critical Path Method
An algorithm for scheduling a set of project activities
Why we need it? It provides us with:
  Project finish date
  Activities that can float in the schedule
  Activities that cannot float - RISK
CPM
Notes: Used to calculate project finish date
To identify to what extent each activity in the schedule can slip (float) without delaying the project
To identify the activities with the highest risk that cannot slip without changing the project finish date

## Slide 25: Critical Path Method - Inputs
What do we need to use CPM?
Network diagram including relations among activities
Activities duration estimates
Demands for resources for each activity
Key dates
Notes: First two can be in Gannt chart

## Slide 26: CPM – how to describe a nod (an activity)
ES – early start - the earliest date a task can start
EF – early finish - the earliest date a task can be completed
LS – late start - the latest date a task can start without delaying the project finish date
LF – late finish - the latest date a task can finish without delaying the project finish date
ES | Total float | EF
Duration (days) | Activity | 
LS | Free float | LF

## Slide 27: Critical Path Method
How to calculte the project´s finish date?
Forward pass calculation (Early Start and Early Finish) – searching for a maximum of early finish of immediate predessesors = early start of an activity
Backward pass calculation (Late Start and Late finish) – searching for a minimun of early start of immediate successors = late finish of an activity

## Slide 28: CPM example
A
2
Finish
Start
F
2
D
6
B
5
E
4
C
1
Forward pass (early start+duration= early finish) – searching for a maximum of early finish of immediate predessesors = early start of an activity
Backward pass – searching for a minimun of early start of immediate successors = late finish of an activity
Notes: Forward pass (early start+duration= early finish) – searching for a maximum of early finish of immediate predessesors = early start of an activity
Backward pass – searching for a minimun of early start of immediate successors = late finish of an activity

## Slide 29: CPM example
Check www.lucidchart.com

## Slide 30: Why are we doing this? 
The purpose of backward pass is to find a float
  Float (slack) – the amount of time an activity can be delayed or lenghtened
  Total float – the amount of time an activity can be delayed without extending the overal project´s completion time
  Free float - the amount of time an activity can be delayed without delaying the early start date of its subsequent tasks

## Slide 31: Total Float
What is the total float for activity A in our example?
Total float – the amount of time an activity can be delayed without extending the overal project´s completion time
Notes: What is the maximum available time for activity A to flow without impact on project completion date?

## Slide 32: Total Float: CPM example
What is the total float for activity A in our example?
Total float – the amount of time an activity can be delayed without extending the overal project´s completion time
Notes: Total float for activity A = 8

## Slide 33: Total Float
Total float – the amount of time an activity can be delayed without extending the overal project´s completion time
TF=LF-EF
TF=LF-ES-D
TF=LS-ES
ES | Total float | EF
Duration (days) | Activity | 
LS | Free float | LF
Notes: TF=LF-EF=LF-(ES+D)=LF-ES-D=
=LF-D-ES=LS-ES

## Slide 34: Free Float
What is the free float for activity A in our example?
Free float - the amount of time an activity can be delayed without delaying the early start date of its subsequent tasks
Notes: How much can activity A be delayed without having any impact on the early start of activity B?

## Slide 35: Free Float: CPM example
What is the free float for activity A in our example?
What about activity C and D?
Free float - the amount of time an activity can be delayed without delaying the early start date of its subsequent tasks
Notes: Free float of activity A = 3
C=5
D=0

## Slide 36: Critical Path Method
Why floats are important in CPM?
Critical activities have the least amount of flow
Floats determine the critical path
If an activity has a TF=0, what does it mean?
Notes: If an activity has a TF=0, what does it mean?
There is no room for delay in that activity – delay extends duration of the whole project. It is a CRITICAL ACTIVITY.
Floats determine the criticallity of an activity.

## Slide 37: Critical Path
Is made of activities that cannot be deayed without delaying the whole project
Items on critical path have zero float
Path with longest duration
Can be more than one

## Slide 38: Can you find the critical path?

## Slide 39: Yes, you can

## Slide 41: Plánování času a zdrojů
Optimalizace plánu
Konflikty zdrojů
Fast-tracking
Crashing
Resource Leveling
Resource Smoothing

## Slide 43: Na co si dát pozor
syndrom studenta (boj s prokrastinací)
milníky a tasky
s kým odhadujete a řešíte rizika  - diverzifikace
rezervy (někdy je třeba je schovat;-)
…

## Slide 44: Analýza a řízení rizik
Co je riziko?
blog.sandglaz.com
www.hypebot.com

## Slide 45: Analýza a řízení rizik
každý projekt má určité množství rizik, se kterými je třeba pracovat (a spoustu, se kterými to třeba není)
risk management neboli řízení rizik – identifikace, analýza a zvolení strategie/práce s rizikem
cílem je minimalizace negativních rizik a snaha o využití pozitivních

## Slide 47: Identifikace rizika
co může nejít podle plánu? Co se může pokazit? Jaké jsou příležitosti?
externí, interní
zdroje informací: minulé projekty (je k dispozici?), myšlenkové mapy, etc.
jasná formulace rizika
hrozba – scénář - dopad
Analýza rizik

## Slide 50: Práce s riziky
Vyhnout se
Přesunout, sdílet
Zmírnit
Akceptovat
„Plán B“

## Slide 51: 3. část
Realizace a ukončení projektu

## Slide 52
Realizace a kontrola

## Slide 53: Realizace projektu
Plán projektu schválen
Rozpočet, harmonogram, WBS – baseline
Plány – rizika, zainteresované strany
Kick-off meeting
  “If everything seems under control, you're not going fast enough.” (M. Addretti, winner of the 1978 Formula One World Championship)

## Slide 54: Realizace projektu
Reportování
Srovnávání skutečnosti s plánem
  Procenta dokončenosti
  Project status/stage
  Milestones trend analysis
  Earned Value Management (EVM)
Notes: Percentage
– often not precise (what does it mean 30% ready? 30% of work, budget, time? Need to specify!)
Careful about 80% of the work ready in three days – tha remaining 20% can last 2 weeks…
P. Status
– e.g. 0-50-100, 0-W-100 (working), 0-50-90-100 (90 until accepted)
Milestones
– setting up a number of milestones, that will be controlled – two times more milestones than usual
Milestone – a control point on the time axis

## Slide 55: Earned Value Management - EVM
A way to measure and evaluate the project performance
Compares the amount of work planned with what is actually accomplished to determine whether the project is on the track
Appropriate for projects with more or less stable scope (investment property construction etc.)
Notes: Can be done in MS Project

## Slide 56: EVM: Planned Value
Planned value (PV)
the planned cost of work scheduled to be done in a given time period
Notes: The first step in earned value analysis is to determine the following three key values:
- Planned value (PV) is the planned cost of work scheduled to be done in a given time period.
- The amount of PV is determined by totaling the cost estimates for the activities scheduled to be completed in the time period.
Planned value is also called the budgeted cost of work scheduled (BCWS).

## Slide 57: EVM: Planned value
EXAMPLE
According to the plan, 3 employees should work on the task for 12 days.
Control time: after 6 days
Planned value (at a control time) is _____ mandays.
Notes: 18
Graph

## Slide 58: EVM: Earned Value
Earned value (EV)
the planned cost of work actually performed in a given time period
the amount of EV is determined by totaling the cost estimates for the activities that were actually completed in the time period.
EXAMPLE: According to the plan, 3 employees should work on the task for 12 days.
75% of the task is ready on the control day 6.
Earned value is _____ mandays.
Notes: Earned value is also called the budgeted cost of work performed (BCWP).
27

## Slide 59: EVM: Actual cost
Actual cost (AC)
determined by totaling the expenditures for the work performed in a given time period
EXAMPLE
According to the plan, 3 employees should work on the task for 12 days.
Report from the responsible employee (on a control day 6): “We worked on the task according to the plan, but one colleague fell ill the third day. So from the fourth day there are only two of us working on the task.”
Actual cost is ______ mandays.
Notes: Actual cost (AC)
The amount of AC is determined by totaling the expenditures for the work performed in a given time period.
It should include only the types of costs included in the budget.
Actual cost is also called the actual cost of work performed (ACWP).
How to find out what is completed? 
15

## Slide 60: PV, EV, AC
USEFUL TEMPLATE: http://www.vertex42.com/ExcelTemplates/earned-value-management.html

## Slide 61: VARIANCES
Schedule variance (SV) the difference between the planned and the actual work completed
SV=EV-PV
Ahead/behind the schedule?
Cost variance (CV)
the difference between the planned cost and the actual cost of work completed
CV=EV-AC
Under/over the budget?
Notes: Schedule variance (SV).
Schedule variance is determined by subtracting the planned value from the earned value.
This calculation measures the difference between the planned and the actual work completed.
A positive result means the project is ahead of schedule; a negative result means the project is behind schedule. SV = EV − PV =27-18=9 days ahead
Cost variance (CV). Cost variance is determined by subtracting the actual cost from the earned value.
It measures the difference between the planned (budgeted) cost and the actual cost of work completed.
A positive result means the project is under budget; a negative result means the project is over budget. CV = EV − AC =27-15=12 mandays spared

## Slide 62: INDEXES
SPI – schedule performance index
a ratio of work performed to work scheduled
this ratio is a measure of efficiency in the schedule
SPI=EV/PV
SPI<1 ….. a project is behind the schedule
SPI>1 ….. a project ahead of schedule
Notes: Schedule performance index (SPI).
This ratio is a measure of efficiency in the schedule.
A value less than 1 means the project has accomplished less than what was planned and is behind schedule; a value greater than 1 means the project is ahead of schedule.
Analyzing the SPI several times during the project provides an indication of how the project is performing compared to the project plan.
This index may also be used to forecast the project completion date.

## Slide 63: INDEXES
CPI – cost performance index
a ratio of budgeted costs to actual costs
this ratio is a measure of cost efficiency
CPI=EV/AC
CPI<1…..the work is costing more than planned
CPI>1…..the work is being produced for less than planned
Notes: Cost performance index (CPI).
This is a ratio of budgeted costs to actual costs. This ratio is a measure of cost efficiency (how efficiently dollars are being spent).
A value less than 1 means the work is costing more than planned; a value greater than 1 means the work is being produced for less than planned.
For example, a CPI of 0.67 means that for each $1.00 spent on the project, the result is $0.67 worth of value.
Analyzing the CPI several times during the project provides an indication of the project’s direction concerning costs.

## Slide 64: INDEXES
Provide a quick snapshot of the project´s efficiencies at a given point in time
More valuable when used periodically
Used for forecasting:
  Budget at completion (BAC) - from WBS
  Estimate to complete (ETC)=(BAC-EV)/CPI
  Estimate at completion (EAC)=AC+ETC
  To complete performance index (TCPI)=(BAC-EV)/(BAC-AC)

## Slide 65: EVM Exercise
The Project was scheduled to cost €1,500 and was originally scheduled to be completed today. As of today, however, the project has spent €1,350, and it is estimated that only two-thirds of the work has been completed. Calculate the schedule and cost variances and the schedule and cost indices.
SV=
CV=
CPI=
SPI=
Notes: PV=1500
AC=1350
EV=1000
SV=EV-PV=-500
CV=EV-AC=-350
CPI=EV/AC=1000/1350=0,74
SPI=EV/PV=1000/1500=0,66

## Slide 66: Limitations
Quantification of project plan is required (x SW, research)
Project accounting is a necessary prerequisity
90-90 rule
Discretization error
https://www.pmconsulting.cz/pm-wiki/evm-earned-value-management/

## Slide 67
Ukončení projektu

## Slide 68: Ukončení projektu
Plánované × předčasné ukončení projektu
Akceptace
Předání výsledku projektu
Benefity – měření – později (po projektu)
Hodnocení průběhu projektu + lessons learned

## Slide 69: Příklady projektů
Olkiluoto Nuclear Power Plant
BER Airport
New Coke
Elbphilharmonie Hamburg
Hoover-dam

## Slide 70: Připomenutí testového úkolu na bloku 3
= úkol na analýzu rizik

## Slide 71: Děkujeme! Máte otázky?
Sylva Žáková Talpová Jan Žák
talpova@econ.muni.cz erwin@email.cz