## RACI Chart
Activity | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I)
Solution Analysis and Design | Dev | PO, Architects | QA, UX, SRE | Team Manager, PM
Implementation | Dev | PO | Architects, SRE, UX | Team Manager, PM, Architects
Testing | QA | PO | Dev, SRE | Team Manager, PM
Documentation creation | Dev, QA | PO, Team Manager | SRE, UX | PM
Gamedays organization | SRE, Dev | PO, Team Manager | QA | PM
Deployment | SRE, Dev | PO, Team Manager | QA | PM
Technical issues resolution | Dev | PO | QA, SRE, Architects | Team Manager, PM
Stakeholder feedback collection | PO, Team Manager, PM | PO, Team Manager | UX | Dev, QA
Third-party library security handling | Dev, SRE, QA | PO, Team Manager | Architects | PM