## TOP Risks
Name | Category | Likelihood | Severity | Mitigation Strategies | Completed
Data Breach | Security | Medium | High | -- Implement role-based access control and the principle of least privilege (PoLP). -- Regular security audits and penetration testing. | YES
Performance Bottlenecks in Large-Scale Environments | Technical | High | High | -- Implement auto-scaling with predefined resource thresholds. -- Optimize database queries (use indexes, partitioning, caching with Redis). -- Conduct load testing and performance benchmarking regularly. | YES
Dependency on other Services | Technical | Medium | High | -- Establish communication channels with other teams. -- Implement automated service health checks and monitoring for dependent services. -- Build fallback mechanisms (e.g., caching, retries, circuit breakers) in case of service unavailability or delays. -- Define clear ownership and responsibility for critical services across teams. -- Regularly test dependencies and ensure proper versioning and compatibility management. | YES
Failure in Report Computation Due to Complex Logic | Technical | Medium | High | -- Optimize and refactor the computation algorithm to improve efficiency. -- Implement asynchronous processing with worker queues (Kafka) -- Improve logging and error handling to detect and recover from failures quickly. | YES
Security Vulnerabilities in Third-Party Dependencies | Security | High | High | -- Automate dependency vulnerability scanning (Dependabot, AWS ECR scan). -- Implement strict versioning and dependency audits. -- Conduct manual security code reviews for critical components. | YES
Lack of Knowledge and Limited Expertise in Legacy Feature | Resource | High | High | -- Implement comprehensive documentation and knowledge-sharing sessions. -- Ensure code is refactored into more maintainable structures. -- Encourage cross-training among team members to eliminate silos. | YES
Insufficient Logging and Monitoring | Operational | Medium | High | -- Implement centralized logging (AppOptics). -- Set up real-time alerting (Slack, email) and anomaly detection. -- Conduct regular log analysis and auditing. | YES